## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | AmruthaVarshini | 2025-12-19 | Retrieved document chunks were not always relevant for certain user queries | Sprint 2 | Self | Logical | 2025-12-20 | Closed | Retrieval relevance improved
2 | AmruthaVarshini | 2025-12-22 | Generated answers did not include proper source citations for some responses | Sprint 3 | Self | Standards | 2025-12-23 | Closed | Citation issue resolved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others